# Project Cost Baseline

Cost Control by Phase and Cost Category

Baseline budget and approved changes for tracking cost variance

## 1. Project Overview

| Project | Horizon ERP Implementation |
| --- | --- |
| Project Manager | Kristina Smirnova |
| Date | 2026-10-24 |
| Monetary unit (currency and scale) | USD |

## 2. How to Use

Enter original costs by category. Record all changes only in the change request register. Only Approved requests with a decision date and approver affect the revised baseline; pending and rejected requests are excluded. Use one currency and monetary scale throughout.

## 3. Cost Baseline

| ID | Phase | Cost Category | Owner | Original Baseline | Approved Changes | Revised Baseline | Actual | Actual Variance | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CB-01 | Design | Contractors | Anna | 2,400,000 | 200,000 | 2,600,000 | 1,870,000 | -730,000 | Approved |
| CB-02 | Implementation | Licenses | Michael | 1,300,000 | -50,000 | 1,250,000 | 990,000 | -260,000 | Approved |
| CB-03 | Launch | Training | Svetlana | 450,000 | 0 | 450,000 | 150,000 | -300,000 | Review |

## 4. Budget Change Request Register

| No. | Request ID | Baseline Item ID | Change Reason | Change Amount | Request Date | Decision Date | Approver | Request Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | CR-001 | CB-01 | Additional ERP integration scope | 200,000 | 2026-10-08 | 2026-10-12 | Irina Petrova | Approved |
| 2 | CR-002 | CB-02 | Agreed license discount | -50,000 | 2026-10-09 | 2026-10-14 | Irina Petrova | Approved |
| 3 | CR-003 | CB-03 | Additional employee training | 100,000 | 2026-10-18 |  |  | Review |
| 4 | CR-004 | CB-02 | Extra user seats | 80,000 | 2026-10-20 | 2026-10-22 | Irina Petrova | Rejected |
| 5 |  |  |  |  |  |  |  |  |
| 6 |  |  |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |  |  |