## Overview
Project Information
PMHub.me
Parameter | Value
Project | Horizon ERP Implementation
Project Manager | Kristina Smirnova
Date | 2026-10-24
Monetary unit (currency and scale) | USD
The original baseline remains unchanged. The Approved Changes column is calculated from the change request register.
Only Approved requests with both a decision date and an approver affect the baseline.
Use the currency and scale specified in the project overview.
Worksheet navigation
Cost Baseline
Change Requests
Dashboard

## Cost Baseline
Project Cost Baseline
PMHub.me
ID | Phase | Cost Category | Owner | Original Baseline | Approved Changes | Revised Baseline | Actual | Actual Variance | Status
CB-01 | Design | Contractors | Anna | 2400000 | 200000 | 2600000 | 1870000 | -730000 | Approved
CB-02 | Implementation | Licenses | Michael | 1300000 | -50000 | 1250000 | 990000 | -260000 | Approved
CB-03 | Launch | Training | Svetlana | 450000 | 0 | 450000 | 150000 | -300000 | Review

## Change Requests
Budget Change Request Register
PMHub.me
No. | Request ID | Baseline Item ID | Change Reason | Change Amount | Request Date | Decision Date | Approver | Request Status
1 | CR-001 | CB-01 | Additional ERP integration scope | 200000 | 2026-10-08 | 2026-10-12 | Irina Petrova | Approved
2 | CR-002 | CB-02 | Agreed license discount | -50000 | 2026-10-09 | 2026-10-14 | Irina Petrova | Approved
3 | CR-003 | CB-03 | Additional employee training | 100000 | 2026-10-18 |  |  | Review
4 | CR-004 | CB-02 | Extra user seats | 80000 | 2026-10-20 | 2026-10-22 | Irina Petrova | Rejected
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
Positive amounts increase the budget; negative amounts decrease it. Retain all requests for audit.
Only Approved requests with a decision date and approver change the revised baseline.

## Dashboard
Entry Status Summary
PMHub.me
Summary uses the source register. Edit records on the source worksheet.
Total records |  | Categories
3 |  | 2
Distribution by category
Draft | 0
Approved | 2
Review | 1