# Software Release Plan

Scope, Milestones and Release Execution

Document release scope, owners, delivery gates, acceptance criteria and rollback.

## 1. Project Overview

| Project | Horizon Customer Portal Launch |
| --- | --- |
| Project Manager | Kristina Smirnova |
| Date | 2026-10-24 |
| Product Version | 2.4.0 |
| Release Date | 2026-11-12 |
| Release Scope | SSO, request tracking and notifications |
| Go/No-Go Decision | Pending decision |

## 2. Purpose and Instructions

Define release scope, check each gate and rehearse rollback. Confirm communications and a go/no-go decision before production rollout.

## 3. Release Activities

| ID | Phase | Activity | Owner | Deadline | Acceptance Criterion | Dependency | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| REL-01 | Preparation | Code Freeze | Tech Lead | 2026-11-02 | All critical pull requests merged | Test completion | Done |
| REL-02 | Validation | Acceptance Testing | QA Lead | 2026-11-03 | No open P0/P1 defects | Release build | In Progress |
| REL-03 | Decision | Go/No-go Review | Release Manager | 2026-11-04 | All workstream leads approved | UAT and runbook | Not Started |
| REL-04 | Release | Production Deployment | DevOps Lead | 2026-11-05 | Smoke tests passed; metrics stable | Approved go/no-go | Not Started |

## 4. Readiness Gates

| ID | Criterion | Owner | Evidence | Status |
| --- | --- | --- | --- | --- |
| G-01 | P0/P1 defects closed | QA Lead | QA report #118 | Done |
| G-02 | Rollback plan approved | DevOps Lead | Runbook #48 | In Progress |
| G-03 | Go/no-go approved | Kristina Smirnova | Decision record | Not Started |

## 5. Risks and Dependencies

| ID | Risk | Response Plan | Owner | Status |
| --- | --- | --- | --- | --- |
| R-01 | SSO API dependency | Validate fallback sign-in | Tech Lead | In Progress |

## 6. Rollback Plan

| ID | Rollback Step | Rollback Trigger | Owner | Status |
| --- | --- | --- | --- | --- |
| RB-01 | Route traffic to prior version | Sign-in failure | DevOps Lead | Done |

## 7. Release Readiness Gates

[  ]  Critical defects resolved

[  ]  Rollback procedure approved

[  ]  Communications approved

## 8. Release Approval

Release Manager: _______________________     Date: __________

QA Lead: _______________________     Date: __________