## Overview
Project Information
PMHub.me
Parameter | Value
Project | Horizon Customer Portal Launch
Project Manager | Kristina Smirnova
Date | 2026-10-24
Product Version | 2.4.0
Release Date | 2026-11-12
Release Scope | SSO, request tracking and notifications
Go/No-Go Decision | Pending decision
Define release scope, check each gate and rehearse rollback. Confirm communications and a go/no-go decision before production rollout.
Worksheet navigation
Release Activities
Readiness Gates
Risks and Dependencies
Rollback Plan
Dashboard

## Release Activities
Software Release Plan
PMHub.me
ID | Phase | Activity | Owner | Deadline | Acceptance Criterion | Dependency | Status
REL-01 | Preparation | Code Freeze | Tech Lead | 2026-11-02 | All critical pull requests merged | Test completion | Done
REL-02 | Validation | Acceptance Testing | QA Lead | 2026-11-03 | No open P0/P1 defects | Release build | In Progress
REL-03 | Decision | Go/No-go Review | Release Manager | 2026-11-04 | All workstream leads approved | UAT and runbook | Not Started
REL-04 | Release | Production Deployment | DevOps Lead | 2026-11-05 | Smoke tests passed; metrics stable | Approved go/no-go | Not Started

## Readiness Gates
Readiness Gates
PMHub.me
ID | Criterion | Owner | Evidence | Status
G-01 | P0/P1 defects closed | QA Lead | QA report #118 | Done
G-02 | Rollback plan approved | DevOps Lead | Runbook #48 | In Progress
G-03 | Go/no-go approved | Kristina Smirnova | Decision record | Not Started

## Risks and Dependencies
Risks and Dependencies
PMHub.me
ID | Risk | Response Plan | Owner | Status
R-01 | SSO API dependency | Validate fallback sign-in | Tech Lead | In Progress

## Rollback Plan
Rollback Plan
PMHub.me
ID | Rollback Step | Rollback Trigger | Owner | Status
RB-01 | Route traffic to prior version | Sign-in failure | DevOps Lead | Done

## Dashboard
Status Summary
PMHub.me
Summary uses the source register. Edit records on the source worksheet.
Total records |  | Categories
4 |  | 3
Distribution by category
Not Started | 2
In Progress | 1
Done | 1
Blocked | 0