## Overview
Project Information
PMHub.me
Parameter | Value
Project | Horizon Customer Portal Launch
Project Manager | Kristina Smirnova
Date | 2026-10-24
Record product initiatives with approved timing and measurable outcomes. Revisit priorities regularly; status labels are set manually.
Worksheet navigation
Initiatives
Period Roadmap
Dashboard

## Initiatives
Product Roadmap
PMHub.me
ID | Theme | Initiative | Expected Outcome | Owner | Time Horizon | Milestone | Status | Priority | Dependency | Target Date
RM-01 | Self-service | Customer Account Portal | Reduce support contacts | Product Lead | Q4 2026 | Closed pilot on Nov 15 | In Progress | High | SSO API | 2027-01-31
RM-02 | Onboarding | Five-minute Initial Setup | Increase activation rate | UX Lead | Q1 2027 | Prototype validation | Planned | High | CRM API | 2027-04-30
RM-03 | Reliability | Critical API Monitoring | Reduce detection time | SRE Lead | Q4 2026 | Metrics review | Completed | Medium | Event service | 2027-07-31

## Period Roadmap
Period Roadmap
PMHub.me
ID | Initiative | Q1 | Q2 | Q3 | Q4
RM-01 | Customer Account Portal | In Progress
RM-02 | Five-minute Initial Setup |  | Planned
RM-03 | Critical API Monitoring |  |  | Planned

## Dashboard
Status Summary
PMHub.me
Summary uses the source register. Edit records on the source worksheet.
Total records |  | Categories
3 |  | 3
Distribution by category
Planned | 1
In Progress | 1
Completed | 1
At Risk | 0