## Overview
Project Information
PMHub.me
Parameter | Value
Project | Horizon Customer Portal Launch
Project Manager | Kristina Smirnova
Date | 2026-10-24
Start with the user goal, break the journey into activities and stories, then assign priority and delivery slice. This is a structured spreadsheet, not an interactive drag-and-drop board.
Worksheet navigation
Story Map
Release Slices
Dashboard

## Story Map
User Story Map
PMHub.me
ID | Persona | Activity | User Task | User Story | Linked Story | Priority | Release Slice | Acceptance Criterion | Status
US-01 | Customer | Sign In | Sign in | As a customer, I want to sign in with email |  | Must | MVP | Successful login and error message | Done
US-02 | Customer | Search | Submit request | As a customer, I want to filter orders | US-01 | Must | MVP | Filter by date and status | In Progress
US-03 | Customer | Track | View status | As a customer, I want to see order history | US-02 | Should | R2 | Change history available | Backlog
US-04 | Administrator | Support | Receive notification | As an agent, I want to view support tickets | US-03 | Could | R2 | Customer profile includes ticket history | Backlog

## Release Slices
Release Slices
PMHub.me
No. | Release Slice | Slice Goal | Stories | Status
1 | MVP | Login, request, status | US-01, US-02, US-03 | In Progress
2 | R2 | Notifications | US-04 | Backlog
3
4
5
6
7
8
9
10

## Dashboard
Status Summary
PMHub.me
Summary uses the source register. Edit records on the source worksheet.
Total records |  | Categories
4 |  | 3
Distribution by category
Backlog | 2
In Progress | 1
Done | 1
Blocked | 0