## Overview
Project Information
PMHub.me
Parameter | Value
Project | Horizon Customer Portal Launch
Project Manager | Kristina Smirnova
Date | 2026-10-24
Track every check with an owner and evidence. Agree on rollback steps and go/no-go gates before deploying.

## Deployment Checks
DevOps Deployment Checklist
PMHub.me
ID | Phase | Check | Owner | Evidence | Due Date | Status | Notes | Result | Completed Date
DEP-01 | Backup | Latest backup verified | DevOps Lead | Checklist #110 | 2026-11-12 | Done |  | Verified | 2026-11-11
DEP-02 | Security | Secrets and access checked | DevOps Lead | Checklist #111 | 2026-11-12 | Done |  | Verified | 2026-11-11
DEP-03 | Environment | Configuration and environment validated | DevOps Lead | Checklist #112 | 2026-11-12 | Done |  | Verified | 2026-11-11
DEP-04 | Database | Database migrations tested in staging | DBA |  | 2026-11-12 | In Progress |  | Pending verification
DEP-05 | Deployment | Production build validated | DevOps Lead |  | 2026-11-12 | In Progress |  | Pending verification
DEP-06 | Smoke tests | Login and request creation verified | DevOps Lead |  | 2026-11-12 | Not Started |  | Pending verification
DEP-07 | Monitoring | Metrics and alerts active | DevOps Lead |  | 2026-11-12 | Not Started |  | Pending verification
DEP-08 | Rollback | Rollback plan ready | DevOps Lead |  | 2026-11-12 | Not Started | Rollback on P0 | Pending verification
DEP-09 | Post-deployment | Post-release stability checked | DevOps Lead |  | 2026-11-12 | Not Started |  | Pending verification
DEP-10 | Sign-off | Final sign-off recorded | Kristina Smirnova |  | 2026-11-12 | Not Started |  | Pending verification

## Dashboard
Status Summary
PMHub.me
Summary uses the source register. Edit records on the source worksheet.
Total records |  | Categories
10 |  | 3
Distribution by category
Not Started | 5
In Progress | 2
Done | 3
Blocked | 0